# Plan of Action

Ration Shop Monitoring and Redistribution System

Team: Sachin S S (23BLC1235) · Keerthanan I (23BLC1246) · Anirudh Ramesh (23BLC1304)

Guide: Dr. V. Pandiyaraju

Document date: 21 August 2026

Status baseline: Panel Review 1 completed. Prototype build phase beginning.

Source: Derived from context.md and Panel_Review_1.pptx (project knowledge base)

# 1. Purpose and How to Use This Plan

This document sequences the work needed to take the project from its current state — a reviewed system design (Panel Review 1) — to the full Definition of Done: a physically deployable dispensing unit with a custom PCB, a 3D-printed enclosure, and a complete interactive dashboard. It is organised as a set of ordered phases, each with concrete tasks, deliverables, and the dependencies or decisions that must be resolved before the phase can complete.

The original academic timeline (Stage 1–4, through October 2026) is preserved in Section 3 for continuity with the panel deck, but Section 4 below supersedes it with a realistic, expanded phase plan that accounts for PCB fabrication lead time, enclosure printing, and dashboard build-out — all of which were out of scope for the original 4-stage academic timeline.

Rule for keeping this current: whenever a phase closes or a decision is made, update the Decision Log in context.md (Section 9) and mark the corresponding row in Section 4 of this document.

# 2. Guiding Principles

- Software-first, hardware-parallel: the verification logic (weight + vision + entitlement matching) can be developed and tested on breadboard hardware while PCB and enclosure design proceed in parallel — do not block software work on hardware fabrication.

- De-risk fabrication early: PCB and 3D-printing both have external lead times (fab house turnaround, print queue). Decisions on tooling and vendors should be made in Phase 1, not deferred.

- Protect the novelty boundary: every phase that touches the verification/record layer should be checked against Section 3 of context.md (the novelty claims) so nothing drifts from what was presented and defended at Panel Review 1.

- Test against real conditions early: the vision classifier's biggest risk is training on clean/controlled images and failing in ration-shop lighting. Field-condition data collection should start as early as Phase 2, not be left to final testing.

- Every phase ends with something demoable: even partial hardware integration should produce a demoable artifact (a working module, a sample dashboard screen, a PCB gerber file) so panel review readiness is continuous, not a last-minute scramble.

# 3. Original Academic Timeline (Reference — from Panel Review 1 deck)

| Phase / Timeframe | Tasks & Deliverables | Dependencies / Decisions Needed |
| --- | --- | --- |
| Stage 1 — pre-August | Literature survey, system requirements, and architecture definition. | Completed. |
| Stage 2 — August | Hardware procurement (load cell, camera), dataset collection, model development. | In progress. |
| Stage 3 — September | Model training, weight + vision integration, three-way verification engine. | Depends on Stage 2 dataset and procurement. |
| Stage 4 — October | Hash-chain implementation, server sync, and redistribution module testing. | Depends on Stage 3 verification engine. |

This 4-stage view maps to the academic deliverable only (Section 7 outcomes in context.md — prototype, classifier, log, dashboard-lite, redistribution module, documentation). It does not include PCB fabrication, enclosure design, or a full multi-view dashboard, which were confirmed on 2026-08-21 as part of the true Definition of Done (context.md Section 0). Section 4 below is the expanded plan that carries the project through those extended deliverables.

# 4. Expanded Phase Plan (Definition-of-Done Roadmap)

Phases are numbered for reference, not strict calendar order — Phases 5 (PCB) and 6 (enclosure) run in parallel with Phases 3–4 (software), since fabrication lead time is the long pole. Suggested months assume an August 2026 start; adjust once PCB/enclosure vendor lead times are confirmed (see Phase 1 decisions).

## Phase 0 — Baseline (Completed)

Literature survey (15 sources), problem framing, 5-layer architecture, 7-module breakdown, and the novelty boundary were defined and defended at Panel Review 1. No further action unless panel feedback requires revision.

## Phase 1 — Tooling Decisions & Procurement (August, current)

| Phase / Timeframe | Tasks & Deliverables | Dependencies / Decisions Needed |
| --- | --- | --- |
| Procurement | Order Raspberry Pi 4, load cell + HX711 amplifier, camera module, diffused LED lighting components. Confirm a bill of materials (BOM) for the breadboard prototype. | None — can start immediately. |
| Tooling decisions | Choose PCB design tool (KiCad recommended — free, widely supported by fab houses) and fabrication route (outsourced fab house, e.g. JLCPCB-style service, vs. in-house). Choose enclosure CAD tool (Fusion 360 or FreeCAD) and printing method (FDM vs. resin) and material (PLA for prototype vs. more durable ABS/PETG for field use). | Blocks Phase 5 and Phase 6 start. Should be resolved this phase — see context.md Open Questions. |
| Dashboard stack decision | Choose frontend framework, hosting/deployment target, and auth approach for inspecting officers. Confirm backend framework (FastAPI vs. Flask). | Blocks Phase 7 start. |
| Dataset planning | Define the pilot commodity set (rice, wheat, sugar per PDS scope) and a data collection plan covering both controlled and real ration-shop lighting conditions. | Blocks Phase 2 dataset collection quality. |

## Phase 2 — Dataset Collection & Model Development (August–September)

| Phase / Timeframe | Tasks & Deliverables | Dependencies / Decisions Needed |
| --- | --- | --- |
| Dataset collection | Capture labeled images of each pilot commodity under varied lighting, container, and pour conditions. Include real ration-shop-like conditions, not only controlled lab shots. | Depends on Phase 1 dataset plan and camera hardware in hand. |
| Classifier development | Train a TensorFlow Lite CNN classifier for commodity-type identification (Module M3). Report accuracy and confusion matrix honestly, including edge cases. | Depends on dataset collection reaching sufficient volume/diversity. |
| Weight acquisition module | Implement load cell + HX711 reading on the Raspberry Pi with weight-settle detection (Module M2). Define and document calibration tolerance bands against standard test weights. | Depends on load cell/HX711 hardware procurement (Phase 1). |

## Phase 3 — Verification & Record Layer (September–October)

| Phase / Timeframe | Tasks & Deliverables | Dependencies / Decisions Needed |
| --- | --- | --- |
| Entitlement/authentication (M1) | Integrate Aadhaar/ePoS entitlement fetch (or a simulated stand-in if live Aadhaar integration is not accessible for a student project — flag this explicitly to the guide). | May need a scoping decision with the guide if live Aadhaar access is not feasible; a mock entitlement service may be an acceptable substitute for demo purposes. |
| Verification engine (M4) | Build the rule engine that checks agreement between entitlement (M1), weight (M2), and commodity class (M3); routes mismatches to Flag for Review. | Depends on M1, M2, M3 all producing usable outputs. |
| Tamper-evident record layer (M5) | Implement SQLite local storage with SHA-256 hash-chained transaction logs. Demonstrate that editing a past entry visibly breaks the chain. | Depends on M4 producing transaction outcomes to log. |
| Server sync design | Define the sync protocol and offline-handling behaviour for shops with poor connectivity (currently an open question in context.md). | Should be resolved before Phase 7 dashboard work depends on live sync. |

## Phase 4 — Full Software Integration on Breadboard Hardware (October)

| Phase / Timeframe | Tasks & Deliverables | Dependencies / Decisions Needed |
| --- | --- | --- |
| End-to-end pipeline | Run the complete Authenticate → Measure & Classify → Verify → Log & Sync flow (Section 4.3 of context.md) on breadboard hardware, end to end. | Depends on Phases 2 and 3 modules all functioning individually. |
| Calibration pass | Validate weight tolerance bands and classifier accuracy against the targets defined in Phase 1/2. | Depends on end-to-end pipeline being runnable repeatedly. |

## Phase 5 — Custom PCB (parallel with Phases 2–4, target: schematic by October, fab by November)

| Phase / Timeframe | Tasks & Deliverables | Dependencies / Decisions Needed |
| --- | --- | --- |
| Schematic design | Design schematic integrating HX711/load cell amplifier, Raspberry Pi/microcontroller interfacing, camera module connection, power regulation, LED lighting driver, and status indicators. | Depends on Phase 1 PCB tool decision and a stable breadboard reference circuit from Phase 2. |
| PCB layout | Lay out the board, run design rule checks (DRC). | Depends on schematic sign-off. |
| Fabrication & assembly | Send gerbers to the chosen fab house; assemble and bring up the board; validate against the breadboard prototype. | Fab house turnaround time is an external constraint — order with enough lead time before the November/December integration phase. |

## Phase 6 — 3D-Printed Enclosure (parallel with Phases 2–5, target: design by November, printing by December)

| Phase / Timeframe | Tasks & Deliverables | Dependencies / Decisions Needed |
| --- | --- | --- |
| Enclosure design | Design housing for load cell platform, camera mount with diffused LED lighting, PCB mounting, cable routing, and ventilation if needed. Design for ration-shop counter use: durable, tamper-resistant mounting, easy to clean. | Depends on Phase 1 CAD tool decision and near-final PCB footprint/dimensions from Phase 5. |
| Printing & fit check | Print prototype enclosure, fit-check against the assembled PCB and sensors, iterate as needed. | Depends on Phase 5 PCB physical dimensions being finalised. |

## Phase 7 — Dashboard & Intelligence Layer (November–December)

| Phase / Timeframe | Tasks & Deliverables | Dependencies / Decisions Needed |
| --- | --- | --- |
| Flagged-transaction dashboard (M6) | Build the base dashboard view listing flagged transactions shop-by-shop for inspecting officers, backed by the sync'd server data. | Depends on Phase 3 server sync design and a stream of real flagged transactions from Phase 4 testing. |
| Redistribution module (M7) | Implement consumption-history analysis and a forecasting method (time-series model — choice currently an open question) to produce shortage predictions and transfer recommendations. | Depends on accumulated transaction history from Phase 4 onward; needs enough logged data to forecast against. |
| Full interactive dashboard | Extend the M6 flagged-list view into the full Definition-of-Done dashboard: live shop-unit status, full searchable/browsable transaction log, redistribution recommendations, and flagged transactions in one interface, with drill-down from a flag into the full transaction record and hash-chain position. | Depends on M6 and M7 both producing data to display; depends on Phase 1 dashboard stack decision. |

## Phase 8 — Full System Integration (December)

| Phase / Timeframe | Tasks & Deliverables | Dependencies / Decisions Needed |
| --- | --- | --- |
| Unit assembly | Assemble the fabricated PCB, sensors, and camera into the printed enclosure to produce a self-contained, field-usable dispensing unit (not a breadboard demo). | Depends on Phase 5 (PCB) and Phase 6 (enclosure) both complete. |
| Integration testing | Re-run the full end-to-end pipeline (Phase 4) on the assembled unit; confirm no regression from the breadboard version. | Depends on unit assembly. |

## Phase 9 — Field/Bench Testing & Validation (December–January)

| Phase / Timeframe | Tasks & Deliverables | Dependencies / Decisions Needed |
| --- | --- | --- |
| Calibration validation | Re-verify weight tolerance bands and classifier accuracy on the assembled unit under realistic conditions. | Depends on Phase 8 integration testing. |
| Tamper-evidence demonstration | Prepare a clear demonstration that record tampering breaks the hash chain, for panel review. | Depends on Phase 3 record layer being stable on the assembled unit. |
| Redistribution validation | Validate recommendation output against a realistic (simulated if needed) multi-center consumption dataset. | Depends on Phase 7 module and sufficient transaction volume. |

## Phase 10 — Documentation & Review Preparation (January)

| Phase / Timeframe | Tasks & Deliverables | Dependencies / Decisions Needed |
| --- | --- | --- |
| Documentation | Write up limitations and field conditions to guide future reviews (per context.md Section 7, outcome 7). Finalise the SRS and this plan as living references. | Depends on all prior phases having stable, describable outcomes. |
| Panel review prep | Prepare the next panel review deck, emphasising the PCB and enclosure work as a differentiator beyond typical academic-project scope (per context.md 'Why this matters for framing'). | Coordinate timing with the guide (Dr. V. Pandiyaraju) and the academic review calendar. |

# 5. Open Decisions Blocking Progress

These are carried from context.md Section 10 and repeated here because they gate specific phases above. Resolving them early prevents downstream schedule slip.

- PCB design tool and fabrication route (blocks Phase 5) — recommend deciding in Phase 1.

- Enclosure CAD tool, printing method, and material (blocks Phase 6) — recommend deciding in Phase 1.

- Dashboard tech stack: frontend framework, hosting, and officer auth approach (blocks Phase 7) — recommend deciding in Phase 1.

- Confusion-matrix / accuracy targets for the TFLite classifier (needed before Phase 2 is considered 'done' and before Review 2).

- Exact load-cell calibration tolerance bands (needed before Phase 2/9 validation can be scored objectively).

- Server-side sync protocol and offline-handling approach (blocks Phase 3 completion and Phase 7 dashboard live-status view).

- Redistribution forecasting method / time-series model choice (blocks Phase 7 M7 implementation).

- Whether live Aadhaar/ePoS integration is feasible for a student project, or whether a mocked entitlement service is an acceptable substitute (affects Phase 3 M1 scope) — recommend raising with Dr. V. Pandiyaraju.

# 6. Ownership & Coordination Notes

This plan does not yet assign phases to individual team members (Sachin S S, Keerthanan I, Anirudh Ramesh). Given the parallel tracks — software (Phases 2–4, 7), PCB (Phase 5), and enclosure (Phase 6) — a natural split is one team member leading each hardware track while the third focuses on the dashboard/intelligence layer, with all three collaborating on Phase 3 (verification/record layer) since it is the connective core of the system. Assign explicitly at the next team sync and record the assignment in context.md's Decision Log.

# 7. Change Control

This plan should be treated as a living document. When a phase's scope, timeline, or dependency changes, update the relevant table row here and add a dated entry to context.md Section 9 (Decision Log) explaining what changed and why — do not silently edit history.